## Sheet1
Task | Start Date | End Date | Duaration (Days)
Topic Selection | 2024-09-25 | 2024-09-27 | 2
Literarture Review | 2024-09-28 | 2024-10-28 | 31
Data Selection | 2024-10-01 | 2024-10-07 | 6
EDA | 2024-10-08 | 2024-10-19 | 11
PDM plan preparation | 2024-10-13 | 2024-10-18 | 5
PDM plan presentation | 2024-10-18 | 2024-10-18 | 1
Data Preprocessing | 2024-10-19 | 2024-10-29 | 10
Data Ethics Quiz | 2024-11-21 | 2024-11-21 | 1
Models Implemetation | 2024-10-25 | 2024-11-05 | 11
Models Fine tuning | 2024-11-03 | 2024-11-11 | 8
Models Comparison | 2024-11-11 | 2024-11-21 | 10
Results Analysis | 2024-11-21 | 2024-11-25 | 4
Final Report Preparation | 2024-10-28 | 2024-12-13 | 46
Draft Methodology | 2024-11-14 | 2024-11-14 | 1
Mock Viva | 2024-11-29 | 2024-11-29 | 1
Final Report Preview and Edit | 2024-12-12 | 2024-12-05 | 24
Final Submission | 2025-01-06 | 2025-01-06 | 1
Viva Preparation | 2024-12-18 | 2025-01-21 | 52
Final Viva | 2025-01-21 | 2025-01-21 | 1
Task | SubTask
Topic Selection & Further Study | Topic Confirmation
Literature Review
Data Collection and Preprocessing | Data Selection
EDA
Data Preprocessing
PDM Plan | Preparation
Presentation
Data Ethics | Quiz
Model Fine tuning and Comparison | Model Implementation
Model Fine Tuning
Resuls and Analysis
Model Comparison
Project Report | Preparation
Draft Methodology
Final Report Preview
First Draft Edit
Final Submission
Project Viva | Mock Viva
Viva Preparation
Final Viva